## Project Management Ger's Garage
Project Management - Timeline
Beauty salon |  |  | DURATION (days)
START DATE | END DATE | ACTIVITIES
2019-11-30 | 2019-12-05 | Requirements survey and functional design | 5
2019-12-06 | 2019-12-09 | Project Planning | 3
2019-12-10 | 2019-12-12 | Starts Development environment | 2
Development
2019-12-13 | 2019-12-23 | Front End | 10
2019-12-23 | 2020-01-15 | Back End | 22
2020-01-16 | 2020-01-22 | Database | 6
Documentation
2019-12-15 | 2019-12-17 | Chapter 1: Introduction | 2
2019-12-17 | 2019-12-29 | Chapter 2: Literature Review | 12
2020-01-03 | 2020-01-13 | Chapter 3: System Analysis & Design | 10
2020-01-14 | 2020-01-20 | Chapter 4: Implementation of system | 6
2020-01-21 | 2020-01-25 | Chapter 5: Testing and evaluation | 4
2020-01-26 | 2020-01-27 | Chapter 6: Conclusions and Further Work | 1
2020-01-28 | 2020-01-28 | Appendices | 0
2020-01-29 | 2020-01-30 | Testing and Final Remark of development | 1
2020-01-31 | 2020-02-01 | Management of issues | 1
2020-01-02 | 2020-01-02 | Retesting | 0
2020-02-02 | 2020-02-02 | Submit Project + Documentation | 0
2020-02-06 | 2020-02-06 | Final Presentation | 0
Projects's Name
Beauty Salon
Goal
The main goal of this project is to create a website which allows customers to book a particular service (hair, nails, hair removal and face). I hope I can achieve
Resources
For the testing, I will use the PHPMyAdmin to improve the interaction of my development which is intended to handle the administration of MySQL over the web, also APACHE and MYSQL.
Project Manager
Juliana Garcia Alves